## Sheet1
xCN Number | 123362WC
Name | SD120C-Canopy Variant-Parts, Assembly, Installation and BOM update based on pilot issues
Description | Below parts are updated and refer attached change content for in detail. 1) Cooler and Installation for fan guard 2) HMI Display software 3) Lug wheel assembly 4) Antenna bracket 5) Seat installation 6) Battery installation 7) Decal for lube chart and other information 8) Chassis harness 9) Battery cable connecting battery to starter motor 10) Fuse and relay harness and console harness 11) Handrail installation updated 12) BOS scraper installation bolt updated 13) Machine unloading document 14) Hose clamp source update
Change Notes & Instructions | Responsible: 1) Cooler and Installation for fan guard - Abhilash and Dinesh 2) HMI Display software - Mohan Mittal 3) Lug wheel assembly - Dinesh 4) Antenna bracket - Dinesh 5) Seat installation - Dinesh 6) Battery installation - Dinesh 7) Decal for lube chart and other information - Dinesh 8) Chassis harness - Mohan Mittal 9) Battery cable connecting battery to starter motor - Mohan Mittal 10) Fuse and relay harness and console harness - Mohan Mittal 11) Handrail installation updated - Dinesh 12) BOS scraper installation bolt updated - Dinesh 13) Machine unloading document (No Procurement) - Dinesh 14) Hose clamp source update - Abhilash Purchase / MM / ME / Ops / AM team - Please refer the attached change content PDF in this DCN for the detailed information about each part.
State | Released
Project | 775788-SD120C Tier-3 Asia + LAM
Reason Code | P - Assembly/manufacturing improvement
Affects Machine Spec | N
Affects Regulatory Compliance | N
TFR Number
Degree of Urgency | 2B
Associated Change Request
Associated xCNs
Scrap Account
CHAIN Number
New Parts
Number | xCT Number | View | Type | Name | Design Stage | Version | Target Unit Cost | Spare Part Code | Serviceable | Service Kit | Serial Number Tracking | Phantom | Gathering | End Item
56685461 | 123362WC-001 | Design | VolvoPart | GRILLE;HOOD | P | 01.4 |  |  | N | N | No | N | N | N
56265241 | 123362WC-001 | Design | VolvoPart | PLATE;ANTENNA MOUNTING | P | 01.2 |  |  | N | N | No | N | N | N
56685460 | 123362WC-001 | Design | VolvoPart | GRILLE;SIDE HOOD | P | 01.4 |  |  | N | N | No | N | N | N
56687061 | 123362WC-001 | Design | VolvoPart | MANUAL;MACHINE UNLOADING | P | 01.7 |  |  | Y | N | No | N | N | N
56265240 | 123362WC-001 | Design | VolvoPart | BRACKET;ANTENNA MOUNTING | P | 01.4 |  |  | Y | N | No | N | N | N
56689493 | 123362WC-001 | Design | VolvoPart | BASE PLATE | P | 01.2 |  |  | N | N | No | N | N | N
56324351 | 123362WC-001 | Design | VolvoPart | WHEEL;LH ASSEMBLY;R-1 LUG TREAD | P | 01.5 |  |  | N | N | No | N | N | N
56384481 | 123362WC-001 | Design | VolvoPart | DECAL;LUBE CHART | P | 01.8 |  |  | Y | N | No | N | N | N
Revised Parts
Number | xCT Number | View | Type | Name | Design Stage | Version | Previous Version | Previous Version Design Stage | Production Disposition | Aftermarket Disposition | Spare Part Code | Serviceable | Service Kit | Serial Number Tracking | Phantom | Gathering | End Item | Comments
53389203 | 123362WC-001 | Design | VolvoPart | COOLING PACKAGE;INSTALLATION;CANOPY | P | 05.8 | 04.28 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
53628563 | 123362WC-001 | Design | VolvoPart | WHEEL;RH ASSEMBLY;R-1 LUG TREAD | P | 02.4 | 01.6 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
53872718 | 123362WC-001 | Design | VolvoPart | MATERIAL SCRAPER;MODULAR;INSTALLATION | P | 03.2 | 02.2 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
54681056 | 123362WC-001 | Design | VolvoPart | PIN;PRODUCT IDENTIFICATION NUMBER;INSTALLATION | P | 03.2 | 02.5 | P | None (see comments) | None (see comments) | X | N | N | No | N | N | N
53627168 | 123362WC-001 | Design | VolvoPart | BATTERY;INSTALLATION | P | 04.2 | 03.3 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
56520784 | 123362WC-001 | Design | VolvoPart | WIRING HARNESS;SWITCH TO STARTER MOTOR | P | 02.3 | 01.7 | B | None (see comments) | None (see comments) |  | Y | N | No | N | N | N
55347855 | 123362WC-001 | Design | VolvoPart | DECAL SET;MACHINE | P | 03.5 | 02.2 | P | None (see comments) | None (see comments) | L | Y | N | No | N | N | N
55303282 | 123362WC-001 | Design | VolvoPart | COOLING PACKAGE | P | 02.5 | 01.5 | P | None (see comments) | None (see comments) | L | Y | N | No | N | N | N
54124738 | 123362WC-001 | Design | VolvoPart | TECHNICAL DOCUMENT | P | 03.2 | 02.1 | P | None (see comments) | None (see comments) | X | N | N | No | N | N | N
55275322 | 123362WC-001 | Design | VolvoPart | COMPACTOR;ASSSIST INSTALLATION;CANOPY | P | 05.10 | 04.5 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
53609426 | 123362WC-001 | Design | VolvoPart | DISPLAY;HMI 4.3inches | P | 02.3 | 01.10 | P | None (see comments) | None (see comments) | R | Y | N | No | N | N | N
55475277 | 123362WC-001 | Design | VolvoPart | DECAL;LUBE CHART | P | 02.2 | 01.2 | P |  |  | R | Y | N | No | N | N | N
56020404 | 123362WC-001 | Design | VolvoPart | HOSE CLAMP | P | 02.1 | 01.2 | P | None (see comments) | None (see comments) |  | Y | N | No | N | N | N
53952882 | 123362WC-001 | Design | VolvoPart | RAIL;INSTALLATION | P | 04.5 | 03.2 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
56556872 | 123362WC-001 | Design | VolvoPart | STIFFENING PLATE | P | 02.2 | 01.6 | B | None (see comments) | None (see comments) |  | Y | N | No | N | N | N
56556297 | 123362WC-001 | Design | VolvoPart | FAN GUARD;WELDMENT | P | 02.3 | 01.5 | B | None (see comments) | None (see comments) |  | Y | N | No | N | N | N
54442297 | 123362WC-001 | Design | VolvoPart | DECAL;INSTALLATION;CANOPY | P | 05.3 | 04.1 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
53442359 | 123362WC-001 | Design | VolvoPart | SEAT;INSTALLATION;CANOPY | P | 05.4 | 04.9 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
55416681 | 123362WC-001 | Design | VolvoPart | BATTERY CABLE;INSTALLATION;CANOPY | P | 04.9 | 03.9 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
53941094 | 123362WC-001 | Design | VolvoPart | HYDRAULIC PUMP;PROPULSION | P | 03.2 | 02.2 | P | None (see comments) | None (see comments) | R | Y | N | No | N | N | N
53671659 | 123362WC-001 | Design | VolvoPart | TELEMATICS KIT;NO SAT AT&T;INSTALLATION CANOPY | P | 03.2 | 02.14 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
53277912 | 123362WC-001 | Design | VolvoPart | PIPING;HYDRAULIC INSTALLATION;CANOPY | P | 05.2 | 04.9 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
53628459 | 123362WC-001 | Design | VolvoPart | WHEEL;LUG TREAD INSTALLATION | P | 02.3 | 01.9 | P | None (see comments) | None (see comments) | T | N | N | No | N | N | N
New Documents
Number | xCT Number | Type | Name | Version
56687061 | 123362WC-001 | Engineering Document | MANUAL;MACHINE UNLOADING | 01.2
56689493.DRW | 123362WC-001 | Drawing | BASE PLATE | 01.1
56384481.DRW | 123362WC-001 | Drawing | DECAL;LUBE CHART | 01.10
56685461.DRW | 123362WC-001 | Drawing | GRILLE;HOOD | 01.2
56265241.DRW | 123362WC-001 | Drawing | PLATE;ANTENNA MOUNTING | 01.1
56324351.DRW | 123362WC-001 | Drawing | WHEEL;LH ASSEMBLY;R-1 LUG TREAD | 01.2
56685460.DRW | 123362WC-001 | Drawing | GRILLE;SIDE HOOD | 01.2
56265240.DRW | 123362WC-001 | Drawing | BRACKET;ANTENNA MOUNTING | 01.3
Revised Documents
Number | xCT Number | Type | Name | Version | Previous Version | Comments
56520784 | 123362WC-001 | Engineering Document | WIRING HARNESS;SWITCH TO STARTER MOTOR | 02.2 | 01.1
53671659.DRW | 123362WC-001 | Drawing | TELEMATICS KIT;NO SAT AT&T;INSTALLATION CANOPY | 03.2 | 02.8
56556297.DRW | 123362WC-001 | Drawing | FAN GUARD;WELDMENT | 02.4 | 01.4
54681056.DRW | 123362WC-001 | Drawing | PIN;PRODUCT IDENTIFICATION NUMBER;INSTALLATION | 03.3 | 02.4
56556872.DRW | 123362WC-001 | Drawing | STIFFENING PLATE | 02.2 | 01.4
53389203.DRW | 123362WC-001 | Drawing | COOLING PACKAGE;INSTALLATION;CANOPY | 05.7 | 04.7
53952882.DRW | 123362WC-001 | Drawing | RAIL;INSTALLATION | 04.5 | 03.1
53941094.DRW | 123362WC-001 | Drawing | HYDRAULIC PUMP;PROPULSION | 03.2 | 02.4
55475277.DRW | 123362WC-001 | Drawing | DECAL;LUBE CHART | 02.6 | 01.3
53442359.DRW | 123362WC-001 | Drawing | SEAT;INSTALLATION;CANOPY | 05.4 | 04.12
53628563.DRW | 123362WC-001 | Drawing | WHEEL;RH ASSEMBLY;R-1 LUG TREAD | 02.3 | 01.3
53627168.DRW | 123362WC-001 | Drawing | BATTERY;INSTALLATION | 04.3 | 03.3
55303282.DRW | 123362WC-001 | Drawing | COOLING PACKAGE | 02.4 | 01.3
55416681.DRW | 123362WC-001 | Drawing | BATTERY CABLE;INSTALLATION;CANOPY | 04.7 | 03.7
53628459.DRW | 123362WC-001 | Drawing | WHEEL;LUG TREAD INSTALLATION | 02.3 | 01.4
53872718.DRW | 123362WC-001 | Drawing | MATERIAL SCRAPER;MODULAR;INSTALLATION | 03.2 | 02.2
53609426.DRW | 123362WC-001 | Drawing | DISPLAY;HMI 4.3inches | 02.3 | 01.3
54442297.DRW | 123362WC-001 | Drawing | DECAL;INSTALLATION;CANOPY | 05.5 | 04.5
53277912.DRW | 123362WC-001 | Drawing | PIPING;HYDRAULIC INSTALLATION;CANOPY | 05.6 | 04.5
56020404.DRW | 123362WC-001 | Drawing | HOSE CLAMP | 02.3 | 01.1
55275322.DRW | 123362WC-001 | Drawing | COMPACTOR;ASSSIST INSTALLATION;CANOPY | 05.12 | 04.4
Non Production / Obsolete / RG4 Parts
Number | xCT Number | View | Type | Name | Version | State | Release Target | Spare Part Code | Serviceable | Service Kit | Recommendation Grade | Superseded by
Structure Changes
Parent Number | xCT Number | Type | Old |  |  |  |  | New |  |  |  |  | Find Number | Line Number | Change Type | Backward Compatible | Production Disposition | Aftermarket Disposition | Included in Option:Model_EngineType:Plant | Included in Option Code | Included in Product Variant | Included in Design Unit Variant | Included in Technical Platform | View | Serviceable | Service Kit | Phantom | Gathering | End Item | Comments
|  |  | Child Number | Child Name | Spare Part Code | Quantity | Material | Child Number | Child Name | Spare Part Code | Quantity | Material
55275322 | 123362WC-001 | VolvoPart | [6 empty] | COMPACTOR;ASSSIST INSTALLATION;CANOPY | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,56170568 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | N | N | N | N | N
53671659 | 123362WC-001 | VolvoPart | [6 empty] | TELEMATICS KIT;NO SAT AT&T;INSTALLATION CANOPY | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,53929295 DUMMY;ENDITEM B-RELEASE-BLR;LONG LEAD ITEMS-SD110X,56170568 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | N | N | N | N | N
56265240 | 123362WC-001 | VolvoPart | [6 empty] | BRACKET;ANTENNA MOUNTING |  |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,53929295 DUMMY;ENDITEM B-RELEASE-BLR;LONG LEAD ITEMS-SD110X,56170568 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | 56265241 | PLATE;ANTENNA MOUNTING |  | 1.0 | See Drawing Indication | 1 |  | Added | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | 55292137 | STIFFENER;ANTENNA MOUNTING | X | 2.0 | See Drawing Indication | 2 |  | Added | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | RM59186262 | BAR;BENT BAR STOCK | R | 1.0 | Migrated Material | 3 |  | Added | [8 empty] | Design | Y | N | N | N | N
53389203 | 123362WC-001 | VolvoPart | [6 empty] | COOLING PACKAGE;INSTALLATION;CANOPY | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,53572724 COMPACTOR;PLANNING BOM;SD110NEW,53929295 DUMMY;ENDITEM B-RELEASE-BLR;LONG LEAD ITEMS-SD110X,53462737 COMPACTOR;PLANNING BOM |  |  | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | RM70887385 | SEALING;SEAL DIRAK -209-0214 | R | 1.0 | Migrated Material | 40 |  | Added | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | RM70872320 | SEALING;SEAL BUBBLE - BAFFLE | R | 3.0 | Migrated Material | 41 |  | Added | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | RM96712831 | PLAIN WASHER;8-200HV;DIN7349 | E | 30.0 | See Drawing Indication | RM96712831 | PLAIN WASHER;8-200HV;DIN7349 | E | 33.0 | See Drawing Indication | 42 |  | Quantity | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | RM96727300 | LOCK NUT;M10-8 ALL METAL;ISO7042 | E | 2.0 | Migrated Material | RM96704614 | LOCK NUT;M10-8 NYLON INSERT;ISO7040 | R | 2.0 | Migrated Material | 60 |  | Replaced | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | 56556297 | FAN GUARD;WELDMENT |  | 1.0 | Not Applicable | 70 |  | Added |  | None (see comments) | None (see comments) | [5 empty] | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | 955921 | SPRING WASHER;8.2x14.2x2;Y 2000-3, black | R | 3.0 | See Drawing Indication | 71 |  | Added | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | RM96718820 | HEXAGON SCREW;M8x20-8.8;ISO4017-FULLY THREADED | E | 3.0 | Migrated Material | 72 |  | Added | [8 empty] | Design | N | N | N | N | N
53872718 | 123362WC-001 | VolvoPart | [6 empty] | MATERIAL SCRAPER;MODULAR;INSTALLATION | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,55082917 COMPACTOR;PLANNING BOM;SD120,56170568 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | N | N | N | N | N
|  | VolvoPart | 997477 | HEXAGON SCREW;M20x100, 10.9;Y 1200-3, colour bright/silver ( | R | 8.0 | See Drawing Indication | 997475 | HEXAGON SCREW;M20x80, 10.9;Y 1200-3, colour bright/silver (F | R | 8.0 | See Drawing Indication | 8 |  | Replaced | [8 empty] | Design | Y | N | N | N | N
55347855 | 123362WC-001 | VolvoPart | [6 empty] | DECAL SET;MACHINE | L |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | Y | N | N | N | N
|  | VolvoPart | RM59605915 | DECAL;DECAL, GREASE | R | 5.0 | Migrated Material | RM59605915 | DECAL;DECAL, GREASE | R | 7.0 | Migrated Material | 9 |  | Quantity | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | 16055767 | WARNING DECAL | R | 1.0 | See Drawing Indication | [5 empty] | 41 |  | Deleted | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | 56384481 | DECAL;LUBE CHART |  | 2.0 | See Drawing Indication | 47 |  | Added | [8 empty] | Design | Y | N | N | N | N
54124738 | 123362WC-001 | VolvoPart | [6 empty] | TECHNICAL DOCUMENT | X |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,53572724 COMPACTOR;PLANNING BOM;SD110NEW |  |  | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | 56687061 | MANUAL;MACHINE UNLOADING |  | 1.0 | Not Applicable | 4 |  | Added | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | 55292122 | BRACKET;ANTENNA MOUNTING | R | 1.0 | Not Applicable | 56265240 | BRACKET;ANTENNA MOUNTING |  | 1.0 | Not Applicable | 2 |  | Replaced | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | RM96741038 | WASHER;WASHER, FLAT M8 -OD 16.0,CL 20 | E | 2.0 | Migrated Material | RM96713979 | PLAIN WASHER;8-200HV;DIN7349 | R | 3.0 | Migrated Material | 5 |  | Quantity | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | RM96713185 | HEXAGON SCREW;M8X25-8.8;ISO4017-FULLY THREADED | E | 2.0 | See Drawing Indication | RM96713185 | HEXAGON SCREW;M8X25-8.8;ISO4017-FULLY THREADED | E | 3.0 | See Drawing Indication | 6 |  | Quantity | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | RM96738554 | PLAIN WASHER;5-200HV;ISO7089 | E | 8.0 | Migrated Material | [5 empty] | 11 |  | Deleted | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | RM96714191 | HEXAGON SCREW;M5x20-8.8;ISO4017-FULLY THREADED | E | 4.0 | Migrated Material | [5 empty] | 14 |  | Deleted | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | RM96712773 | HEXAGON NUT;M5-8;ISO4032 | R | 4.0 | Migrated Material | [5 empty] | 17 |  | Deleted | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | RM70927645 | CABLE TIE;STRAP TIE, BLACK, 4.7MMX | R | 16.0 | Migrated Material | RM70927645 | CABLE TIE;STRAP TIE, BLACK, 4.7MMX | R | 18.0 | Migrated Material | 19 |  | Quantity | [8 empty] | Design | Y | N | N | N | N
53952882 | 123362WC-001 | VolvoPart | [6 empty] | RAIL;INSTALLATION | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,53937244 COMPACTOR,54000000 COMPACTOR;PLANNING BOM,56170568 COMPACTOR;PLANNING BOM;SD120C,54663425 COMPACTOR;PLANNING BOM, SD110e |  |  | Design | N | N | N | N | N
|  | VolvoPart | 12822293 | U-BOLT;M10 | R | 1.0 | Migrated Material | [5 empty] | 4 |  | Deleted | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | 12822294 | CLAMPING PLATE;RAIL | X | 1.0 | Migrated Material | 12822294 | CLAMPING PLATE;RAIL | X | 2.0 | Migrated Material | 5 |  | Quantity | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | 60113105 | FLANGE SCREW;M10x100, 10.9;Y 1200-3, colour bright/silver (F | R | 2.0 | See Drawing Indication | 13 |  | Added | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | 14539233 | GROMMET;2 IN | R | 1.0 | CR, VEXM7020 | 14 |  | Added | [8 empty] | Design | Y | N | N | N | N
53628459 | 123362WC-001 | VolvoPart | [6 empty] | WHEEL;LUG TREAD INSTALLATION | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,55082917 COMPACTOR;PLANNING BOM;SD120,56170568 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | N | N | N | N | N
56324351 | 123362WC-001 | VolvoPart | [6 empty] | WHEEL;LH ASSEMBLY;R-1 LUG TREAD |  |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,55082917 COMPACTOR;PLANNING BOM;SD120,56170568 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | 53951021 | WHEEL RIM;DW20B X 26 | R | 1.0 | Not Applicable | 1 |  | Added | [8 empty] | Design | Y | N | N | N | N
|  | VolvoPart | [5 empty] | 12777218 | TIRE;23.1-26 12 PLY BIAS;R-1 LUG TR | X | 1.0 | Migrated Material | 2 |  | Added | [8 empty] | Design | N | N | N | N | N
56556297 | 123362WC-001 | VolvoPart | [6 empty] | FAN GUARD;WELDMENT |  |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,55325713 COMPACTOR;BNG DD25 DUMMY,55082917 COMPACTOR;PLANNING BOM;SD120,53572724 COMPACTOR;PLANNING BOM;SD110NEW,53929295 DUMMY;ENDITEM B-RELEASE-BLR;LONG LEAD ITEMS-SD110X,53462737 COMPACTOR;PLANNING BOM |  |  | Design | Y | N | N | N | N
|  | VolvoPart | 56556298 | BASE PLATE |  | 1.0 | See Drawing Indication | 56689493 | BASE PLATE |  | 1.0 | See Drawing Indication | 1 |  | Replaced | [8 empty] | Design | N | N | N | N | N
55416681 | 123362WC-001 | VolvoPart | [6 empty] | BATTERY CABLE;INSTALLATION;CANOPY | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | N | N | N | N | N
|  | VolvoPart | 55373790 | WIRING HARNESS;SWITCH TO STARTER MOTOR | R | 1.0 | Not Applicable | 56520784 | WIRING HARNESS;SWITCH TO STARTER MOTOR |  | 1.0 | Not Applicable | 3 |  | Replaced |  | None (see comments) | None (see comments) | [5 empty] | Design | Y | N | N | N | N
|  | VolvoPart | RM96741038 | WASHER;WASHER, FLAT M8 -OD 16.0,CL 20 | E | 12.0 | Migrated Material | RM96741038 | WASHER;WASHER, FLAT M8 -OD 16.0,CL 20 | E | 9.0 | Migrated Material | 9 |  | Quantity | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | RM96722103 | HEXAGON SCREW;M8x20-10.9;ISO4017-FULLY THREADED | E | 12.0 | Migrated Material | RM96722103 | HEXAGON SCREW;M8x20-10.9;ISO4017-FULLY THREADED | E | 13.0 | Migrated Material | 10 |  | Quantity | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | RM96712831 | PLAIN WASHER;8-200HV;DIN7349 | E | 4.0 | See Drawing Indication | 13 |  | Added | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | 55292122 | BRACKET;ANTENNA MOUNTING | R | 1.0 | Not Applicable | 56265240 | BRACKET;ANTENNA MOUNTING |  | 1.0 | Not Applicable | 4 |  | Replaced | [8 empty] | Design | Y | N | N | N | N
53277912 | 123362WC-001 | VolvoPart | [6 empty] | PIPING;HYDRAULIC INSTALLATION;CANOPY | T |  | Not Applicable | [8 empty] | 53376728 COMPACTOR;PLANNING BOM;SD120C,53572724 COMPACTOR;PLANNING BOM;SD110NEW,53929295 DUMMY;ENDITEM B-RELEASE-BLR;LONG LEAD ITEMS-SD110X,53462737 COMPACTOR;PLANNING BOM,53236145 COMPACTOR;PLANNING BOM,56170568 COMPACTOR;PLANNING BOM;SD120C |  |  | Design | N | N | N | N | N
|  | VolvoPart | RM96713417 | HEXAGON SCREW;M8x65-8.8;ISO4014-PARTIALLY THREADED | E | 8.0 | Migrated Material | RM96713417 | HEXAGON SCREW;M8x65-8.8;ISO4014-PARTIALLY THREADED | E | 6.0 | Migrated Material | 42 |  | Quantity | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | RM96713086 | HEXAGON SCREW;M8x70-8.8;ISO4014-PARTIALLY THREADED | E | 10.0 | Migrated Material | RM96713086 | HEXAGON SCREW;M8x70-8.8;ISO4014-PARTIALLY THREADED | E | 12.0 | Migrated Material | 43 |  | Quantity | [8 empty] | Design | N | N | N | N | N
|  | VolvoPart | 53628563 | WHEEL;RH ASSEMBLY;R-1 LUG TREAD | T | 2.0 | Not Applicable | 53628563 | WHEEL;RH ASSEMBLY;R-1 LUG TREAD | T | 1.0 | Not Applicable | 1 |  | Quantity |  | None (see comments) | None (see comments) | [5 empty] | Design | N | N | N | N | N
|  | VolvoPart | [5 empty] | 56324351 | WHEEL;LH ASSEMBLY;R-1 LUG TREAD |  | 1.0 | Not Applicable | 4 |  | Added | [8 empty] | Design | N | N | N | N | N
Line Number Changes
Parent Number | xCT Number | Type | Old |  |  |  |  | New |  |  |  |  | Find Number | Line Number | Change Type | Backward Compatible | Production Disposition | Aftermarket Disposition | Included in Option:Model_EngineType:Plant | Included in Option Code | Included in Product Variant | Included in Design Unit Variant | Included in Technical Platform | View | Serviceable | Service Kit | Phantom | Gathering | End Item | Comments
|  |  | Child Number | Child Name | Spare Part Code | Quantity | Material | Child Number | Child Name | Spare Part Code | Quantity | Material
Associated sBOMs
Number | Type | Upstream Part | Out of Date | Name | View | Spare Part Code | Serviceable | Service Kit | Phantom | Gathering | End Item
55303282 | VolvoPart | 55303282, 02.5 | Y | COOLING PACKAGE | Service | L | Y | N | N | N | N
Serial No. / Effectivity
End Item | Model Type | Production Location | Planned Introduction Date | Real Introduction Date | Serial Number Range | Comments
55082917, COMPACTOR;PLANNING BOM;SD120 |  | Bangalore, India
55325713, COMPACTOR;BNG DD25 DUMMY |  | Bangalore, India
53988707, COMPACTION ASPHALT;PLANNING BOM;PT220D |  | Bangalore, India
53989063, COMPACTOR;PLANNING BOM;SD110D2 |  | Bangalore, India
54000000, COMPACTOR;PLANNING BOM |  | Bangalore, India
54813381, COMPACTOR;DD90D PLANNING BOM |  | Bangalore, India
53376728, COMPACTOR;PLANNING BOM;SD120C |  | Bangalore, India
53929295, DUMMY;ENDITEM B-RELEASE-BLR;LONG LEAD ITEMS-SD110X |  | Bangalore, India